## Release Schedule
Music Label Release Schedule Tracker (Feb-Sep 2026)
Artist | Release Title | Type | Territory | Release Date | Delivery Lock | Priority | Status
Golden Harbour | Falling Satellites | Single | Global | 2026-02-07 | 2026-01-19 | High | Assets In
Lena Solis | Midnight Echoes | Single | Global | 2026-03-08 | 2026-02-22 | High | Live
Han Jisoo | Seoul at 2AM | Single | KR/Global | 2026-03-22 | 2026-03-08 | Medium | Assets In
Nightshift Arcade | Pixel Dreams | Single | Global | 2026-04-05 | 2026-03-20 | High | Delivered
Golden Harbour | Static in the Skyline | Single | Global | 2026-04-19 | 2026-04-05 | Medium | Planning
Lena Solis | Glass Heart City | Single | Global | 2026-05-10 | 2026-05-03 | Medium | Assets In
Nightshift Arcade | Starlight Glitch (feat. Nova Calle) | Single | US/EU | 2026-05-24 | 2026-05-17 | High | Delivered
Lena Solis | Confessions | EP | Global | 2026-06-14 | 2026-06-01 | High | Assets In
Han Jisoo | Neon Han River | Single | KR/Global | 2026-07-12 | 2026-07-01 | Low | Planning
Nightshift Arcade | Afterimage Forever | Album | Global | 2026-08-30 | 2026-08-09 | Low | Planning
Golden Harbour | Maps for Nowhere | Album | Global | 2026-09-27 | 2026-09-06 | Medium | Planning
AT-RISK RELEASES (NEXT 7 DAYS): 1
Color | Meaning
Green | Delivered
Red | At-Risk Release

## Metadata & Assets
Metadata & Asset Readiness Tracker (Track-Level)
Track Title | Artist | Release Title | ISRC | UPC | Version | Explicit | Duration | Audio Master Status | Cover Art Status | Metadata Complete | Notes/Issues
Falling Satellites | Golden Harbour | Maps for Nowhere | US-GH1-26-00001 | 889123456801 | Original | No | 3:42 | Received | In Progress | No | Awaiting final artwork approval
Midnight Echoes | Lena Solis | Confessions | US-LS1-26-00001 | 889123456802 | Radio Edit | No | 4:05 | Approved | Approved | Yes | Live on all DSPs
Seoul at 2AM | Han Jisoo | Seoul at 2AM | KR-HJ1-26-00001 | 889123456803 | Original | No | 3:58 | Received | In Progress | No | Audio QC pending
Pixel Dreams | Nightshift Arcade | Afterimage Forever | US-NSA-26-00001 | 889123456804 | Original | No | 3:31 | Approved | Approved | Yes | Delievered to distributor
Static in the Skyline | Golden Harbour | Maps for Nowhere | US-GH1-26-00002 | 889123456801 | Original | No | 3:47 | Not Received | Not Started | No | Awaiting initial asset delivery
Glass Heart City | Lena Solis | Confessions | US-LS1-26-00002 | 889123456802 | Original | No | 4:12 | Received | Approved | No | Metadata credits under review
Starlight Glitch (feat. Nova Calle) | Nightshift Arcade | Afterimage Forever | US-NSA-26-00002 | 889123456804 | Original | No | 3:26 | Approved | Approved | Yes | Feature metadata verified
Confessions | Lena Solis | Confessions | US-LS1-26-00003 | 889123456802 | Instrumental | Yes | 4:29 | Received | Approved | No | Explicit flag confirmation pending
Neon Han River | Han Jisoo | Neon Han River | KR-HJ1-26-00002 | 889123456805 | Original | No | 3:50 | Not Received | Not Started | No | Assets not yet submitted
Afterimage Forever | Nightshift Arcade | Afterimage Forever | US-NSA-26-00003 | 889123456804 | Original | No | 4:41 | Not Received | Not Started | No | Album mastering in progress
Maps for Nowhere | Golden Harbour | Maps for Nowhere | US-GH1-26-00003 | 889123456801 | Original | No | 5:02 | Not Received | Not Started | No | Album delivery timeline TBD
TRACKS NOT DELIVERY-READY: 8

## Delivery & Checklist
Release Delivery & Go-Live Checklist
Artist | Release Title | Release Type | Release Date | Delivery Status | Distributor | Pre-save/Pre-add | Marketing Assets Ready | DSP Links Live | Release Ready | Notes/Risks
Golden Harbour | Falling Satellites | Single | 2026-02-07 | In Progress | TuneCore | Not Started | No | No | No | Awaiting final artwork approval
Lena Solis | Midnight Echoes | Single | 2026-03-08 | Live | AWAL | Live | Yes | Yes | Yes | Live on all DSPs
Han Jisoo | Seoul at 2AM | Single | 2026-03-22 | Not Started | The Orchard | Not Started | No | No | No | Audio QC pending
Nightshift Arcade | Pixel Dreams | Single | 2026-04-05 | Delivered | DistroKid | Live | Yes | No | Yes | Delivered to distributor
Golden Harbour | Static in the Skyline | Single | 2026-04-19 | In Progress | The Orchard | Not Started | No | No | No | Awaiting initial asset delivery
Lena Solis | Glass Heart City | Single | 2026-05-10 | Not Started | AWAL | Not Started | No | No | No | Metadata credits under review
Nightshift Arcade | Starlight Glitch (feat. Nova Calle) | Single | 2026-05-24 | Delivered | DistroKid | Live | Yes | No | Yes | Feature metadata verified
Lena Solis | Confessions | EP | 2026-06-14 | Not Started | AWAL | Not Started | No | No | No | Explicit flag confirmation pending
Han Jisoo | Neon Han River | Single | 2026-07-12 | Not Started | The Orchard | Not Started | No | No | No | Assets not yet submitted
Nightshift Arcade | Afterimage Forever | Album | 2026-08-30 | Not Started | DistroKid | N/A | No | No | No | Album mastering in progress
Golden Harbour | Maps for Nowhere | Album | 2026-09-27 | Not Started | The Orchard | N/A | No | No | No | Album delivery timeline TBD
RELEASES NOT READY: 8 |  |  | LIVE ON DSPs: 1 |  |  |  | RELEASES DUE IN 30 DAYS (NOT DELIVERED): 1
Color | Meaning
Green | Live on DSPs
Yellow | Delivered but not Live
Red | At Risk/Blocking Issue